## Sheet1
CCHF CONFERENCE
Name & Organization
QUESTIONS | ANSWERS
| Tony Cook Company- PCL | Terry Barker Company- Perkins & Will | Susan Sallaj Company-Ottawa Hospital | Bart DeVries Company-Colliers Project Leaders
1. What are some of the key design lessons to avoid? | · Design solutions have to be unique to the project and client. This appears obvious, but too often there is a tendency to fit the client to a pre-conceived design rather than adequately engaging them and understanding their needs. • Do not sacrifice coordination of the various design elements for the sake of speed. The coordination will have to happen before the final construction and it is much more efficient to do this before trades people are standing on site waiting for answers • Do not assume that Revit Models equal coordination. Systems are rarely modeled correctly prior CD stage and insufficient space either in the ceiling or openings for services can lead to delays and re-design | Strategic Design is not just about the physical environment ....Design includes for and is significantly influenced by:- o Design of strategy o Design of Vision o Design of process o Design of the Model of Care o Design of the Technology o Etc..etc.. • The Design of the Building is totally dependent upon and in support of the other design considerations Other major considerations that must be considered and not avoided:- • Engage the right people with the right expertise ..dont settle for whats availiable • Look to work in a collaborative manner using an IPD type of approach • Chose the right procurement type • Spend time defining the scope and clearly communicate and align expectations • Constantly review and ensure that alignment of expectations across the entire team at every stage of the project • Engage the Contractor in the design process as soon as possible (IPD it happens anyway) | • Don't assume anything- items need to be followed up and confirmed. • Undersizing and compromising of support services spaces. • Ensure client sign off of floor plans prior to DD. • Clear, written direction to design team - scope of work is not implied. • Providing context, rationale and vision of common goal and reference point. • Client expectations & understanding of plans - Most client can't read plans nor understand what they are getting ( not their skill set) • Actual apply common sense to the discussion • Front End - Division 0 & 1 - Read the entire front end and customize it appropriately | Closed-in spaces with complicated navigation; wherever possible, replicate the main corridor footprint on each level for ease of wayfinding Going with things that are in “fad” and may not stand the test of time. Paint colours can be easily changed, other design strategies may not be and can be costly to re-work later. Trial key pieces of furniture. Some furniture looks better than it feels – particularly important in patient waiting areas. If furniture in uncomfortable, 10 – 15 years to replace is a long time. Orientation sessions for users prior to full-out engagement in design, design reviews. Help them understand the process and where they will be called upon to provide input. When asking for their input, further education may be necessary (e.g. room data sheets - codes for sinks and how an SS1 is different from an SS2. Process wise – don’t assume buy-in/approval – notify intent and rationale, ask your questions, and find support when necessary. Teams have to work together and go through the issues, can’t avoid tough conversations / decisions Acoustics - and other similar "soft" elements are often overlooked or de-emphasized but count where it matters / confidentiality Ensure spaces have a purpose - watch out for wish list items that don't materialize Millwork in public areas, credenza's in hotelling spaces - no ownership, no use.
Design • What we consider standard practice in today’s healthcare design may have been thought innovated several years ago and obsolete in the next 5-10 years • Technology + Design to accommodate future adaptability (loss fit ) • Greater consideration needs to be given to the environments functionality rather than physical space and look to anticipate change. • Application of a Kit of Parts via the application of a simple robust design rational • Application of standardization, Pre-Fabrication & Modularization (The Greater Accra Regional Hospital at Ridge, Accra, Ghana )
2. What are the most important features to optimize? | N/A | You never get a second Chance to make a first impression:- • Thoughtful design can help ensure the proper first impression is created communicated and sustained Every healthcare facility conveys a message to patients, visitors, volunteers, vendors, and staff. The facility also communicates a barrage of clues about the organization and the medical care being provided there….The clues start at the approach to the facility, the drop-off area, the parking lots, and the street signs. Ideally, that message is one that conveys welcoming, caring, comfort, and compassion, commitment to patient well-being and safety, where… stress is relieved, refuge is provided, respect is reciprocated, competence is symbolized, way-finding is facilitated, and families are accommodated. Not forgetting that the facility also influences employee service attitudes and behaviors. Finishes, signage, and artwork must be carefully selected, well-coordinated, and integrated. Security must also be balanced with some features apparent to patients/visitors, while conveying a message of safety. Considerations:- • Understanding the patient / user journey and experience • Access to daylight for staff and patients • Visual links back to nature and the external environment • Key patient staff nodes • Public / Community spaces | • Natural light. • Flows- work flows, traffic pattern, public flows. • Efficient and flexible spaces • Useful Storage Solution • Natural pauses in space - alcoves, etc... | Space – open and easy to multipurpose Views to exterior, natural light - enabled through high floor to ceiling heights, clerestory and transom glazing, low desk heights, etc. Green space - not in just one area, and not necessarily a lot of it. Think terraces at various levels of the building to compliment ground floor green space. Intuitive design (building easy to navigate) - one main corridor that runs the entire length, punctuated by areas of interest/expression. Do something different (e.g. low window for kids to gaze into courtyard), bench seat in a window, etc. Shared/bookable spaces co-located in an easily accessbile location for staff and public.
3. What are the most impactful constructions innovations that have improved healthcare facilities? | · The changes in procurement methodology to the P3 model has brought the constructor into the projects at a much earlier stage, allowing for constructability reviews and an integrated approach to projects • Standardization and modular construction has improved quality and can offset the challenges of a smaller labour force in some markets • Moving forward the use of computer modeling and VR technology is being used to allow stakeholders to understand the design | Slow realization that Pre-fabrication, Modularization & Standardization can help provide Design, construction and operational efficiencies | • Introduction of P3s- provides the ability to build facilities sooner • Pre- packaged , pre- assembled equipment - welding in shops prior to coming to site • Intelligence devices - addressable systems • LED lighting | Outdoor terraces on each level. Allows for greater options for delivery of service. Creates a softer feel to the building and some elements may even make the building a "destination" (e.g. a superb, custom outdoor playground for kids unlike anything in a local park). Daylight/views Inboard offices - open workstations on perimeter. Realization that it is not just patients who need daylight/views, but staff who spend so many hours in the space do too. Design that follows the Lean methodology
4. Where is the best place to invest money in design? What are the tradeoffs? | · On Renovation/Expansion projects invest the time and money in understanding the existing systems/as-built conditions • Do not rely on previous record drawings alone; site inspections are critical | See answer to Question 1 & 2 above along with:- • Time spent Upfront Planning • Ensure flexibility of use | • Previous projects As-Built, Record drawings • Site Investigations • Constructability Reviews • Commissioning agent involved from design to close out • Trade offs- potentially schedule impacts and money, however, could simply be a re- distribution within the project lifecycle | Get the bones/ infrastructure of the building right… it has to last… and maintenance costs are a burden. Spend the time/money up front. Even if it takes an extra 6 months to go to tender - the benefits will last a half-century. Durable, quality materials/components
5. How do you engage hospital planners to understand the design tradeoffs? | N/A | Encourage better understanding of what the value proposition is for each of the stakeholders Design • Visualizations / digital modelling | • Direction should be provided by the hospital planners to the design team. • Creative discussions are healthy and welcomed | Building relationships, collaborating, being honest with each other. Know each other socially, not just professionally so you are comfortable with these discussions. Touring other sites (together if possible) - to share experiences and decide on outcomes. Full engagement of users of the space is essential – fully engaged and educated users can identify the issues and tradeoffs that will work in the long term – minimizing change requests during and after construction. Too many hospital planners inform rather than truly partner, or better yet, allow users to lead this process.
6. How do you apply strategic thinking to design, knowing that you can’t have it all? | N/A | • Constantly revert to the vision • Regularly review / align expectations • Design with a number of veneers knowing that they will (dependant upon the procurement process) be removed but the original design intent will remain intact | • Must begin with a strong, strategic foundation • Common set of values and clear destination • Items to be measured from common reference point to guide consistent, informed decision making | What aspects have the potential for the most permanent rewards? Focus on them. Be prepared to defend positions you know to be true - know that you are the "expert" in some (but not all!) aspects of the design - yet still allow yourself to be open to changing your mind. Be prepared to challenge ideas that don't have a benefit for others, but only a small group or perhaps an individual. Choose your battles - be confident you can win them with your evidence/rationale - but let it go if someone has a better idea or evidence. Identify principles for decisions, and your priorities, including deal breakers before you start your planning. Don't entertain discussion on things that have already been decided (e.g. siting of the development). Critically analyze before executing - imperative for big or contentious decisions. Prioritize the things that will benefit the most people, and the low cost items with high returns. Research needs - don't assume that current requirements equals future requirement. E.g. complete a storage space assessment to determine what is really required in the new space.
7. Decisions made and lessons learned from them? | N/A | N/A | • Ensure the LL actually get applied to the next project | Hire an AV consultant Consistent players throughout - the "history" is important. Ensure each department has a clinical lead, and that he/she will be given the time required to execute all their tasks. A thorough and thoughtful approach to ergonomics in any fixed workspace is vital, especially in non-traditional work environments (like standing height counters).